## Sheet1
Hubot
Sprint | Week | Date | Day | Class | Class Contents | Meeting | Meeting Idea | Meeting Achievement
1 | 1 | 2017-01-10 | Tu | lecture | group & topic - virtual assistant
|  | 2017-01-12 | Th | lecture | learn phases of project
|  | 2017-01-15 | Su |  |  | Team 1 | Compare differnet kind of virtual assistans | Decision: Hubot is a better option than Alexa
| 2 | 2017-01-17 | Tu | lecture | Presentation 1 standups & Github | Sponsor 1 | SWOT research | Hubot or Alexa
|  | 2017-01-19 | Th | lecture
|  | 2017-01-22 | Su
2 | 3 | 2017-01-24 | Tu | lecture | Presentation 2 standups | Sponsor 2 | New tool - Bot | Bot Framwork Use Introduction
|  | 2017-01-26 | Th | lecture
|  | 2017-01-29 | Su |  |  | Team 2 | ppt progress | discover risks for presentation
| 4 | 2017-01-31 | Tu | lecture | No presentation | Sponsor 3 | project progress | Burn-down-rate demo
|  | 2017-02-02 | Th | lecture
|  | 2017-02-05 | Su
3 | 5 | 2017-02-06 | Mo |  |  | Sponsor 4 + instructor | risk presentation | 2h risk pre-presentation & improvement
|  | 2017-02-07 | Tu | lecture | risk ppt of other groups
|  | 2017-02-09 | Th | lecture | Presentation 3 Risks
|  | 2017-02-11 | Sa |  |  | Team 3 | coding progress | code structures, task assignment
|  | 2017-02-12 | Su |  |  | Team 4 hangouts | Project progress | improvements of Jira
| 6 | 2017-02-14 | Tu | lecture (free time) |  | Sponsor 5 (30 minutes) | presentation feedback: too fast, slide problems | Authenication solutions |  | make standup ppt
|  | 2017-02-16 | Th | lecture (free time) | project progress
|  | 2017-02-19 | Su
4 | 7 | 2017-02-20 | Mo |  |  | Team 5 | Assign tasks for each member on Jira | prepare Branden
|  | 2017-02-21 | Tu | lecture | Presentation 4 standups | Sponsor 6 | authenication solve; add new features |  | 注：group1- finish diagrams in proposal; begin coding
|  | 2017-02-23 | Th | [5 empty] | Group 2- dashboard finish & begin chat
|  | 2017-02-26 | Su | [5 empty] | Group 3 - similar to us
| 8 | 2017-02-28 | Tu
|  | 2017-03-02 | Th
|  | 2017-03-05 | Su
5 | 9 | 2017-03-07 | Tu
|  | 2017-03-09 | Th
|  | 2017-03-12 | Su
| 10 | 2017-03-14 | Tu
|  | 2017-03-16 | Th
|  | 2017-03-19 | Su
6 | 11 | 2017-03-21 | Tu
|  | 2017-03-23 | Th
|  | 2017-03-26 | Su
| 12 | 2017-03-28 | Tu
|  | 2017-03-30 | Th
|  | 2017-04-02 | Su
7 | 13 | 2017-04-04 | Tu
|  | 2017-04-06 | Th
|  | 2017-04-09 | Su
| 14 | 2017-04-11 | Tu
|  | 2017-04-13 | Th
|  | 2017-04-16 | Su
8 | 15 | 2017-04-18 | Tu
|  | 2017-04-20 | Th
|  | 2017-04-23 | Su
| 16 | 2017-04-25 | Tu
|  | 2017-04-27 | Th
|  | 2017-04-30 | Su